## sketch planning schedule
TASKS | 2006-07-06 | 2006-08-06 | 2006-09-06 | 2006-10-06 | 2006-11-06 | 2006-12-06 | 2007-01-07 | 2007-02-07 | 2007-03-07 | 2007-04-07 | 2007-05-07 | 2007-06-07 | 2007-07-07 | 2007-08-07 | 2007-09-07 | 2007-10-07 | 2007-11-07 | 2007-12-01 | 2008-01-01 | 2008-02-01 | 2008-03-01 | 2008-04-01 | 2008-05-01
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
MEETINGS | ■ | ▲ | ▲ | ■ | ▲ | ▲ | ● | ▲ | ● | ● | ▲ | ▲ | ● | ▲ | ● | ● | ▲ | ▲ | ▲ | ■ | ● | ▲ | ■
EARLY ACTIVITIES (EA)
Wisconsin Environmental Scan | bar: 2006-07-06 to 2006-10-06
National Best Practices | bar: 2006-07-06 to 2006-10-06
Project Relations Definition | bar: 2006-07-06 to 2006-10-06
Project Communications and Outreach Plan | bar: 2006-08-06 to 2006-10-06
CORRIDOR PLANNING METHODOLOGY FOR TRAFFIC OPERATIONS (CPM)
System Performance Goals and Criteria | bar: 2006-10-06 to 2006-12-06
Traffic Operations Scenarios Development | bar: 2006-11-06 to 2007-01-07
Corridor Concept of Operations Design | bar: 2006-12-06 to 2007-02-07
Planning Methodology Process Alternatives and Design | bar: 2007-01-07 to 2007-03-07
Develop and Integrate ConOps into Planning Methodology | bar: 2007-10-07 to 2008-02-01
Integration of Infrastructure and M&O Programming | bar: 2008-02-01 to 2008-05-01
RAMP CONTROL AND SURVEILLANCE SKETCH PLAN (RCS)
Develop Criteria | bar: 2006-10-06 to 2006-12-06
Data Collection | bar: 2006-12-06 to 2007-02-07
Apply Criteria | bar: 2007-02-07 to 2007-07-07
Technology Alternatives | bar: 2007-02-07 to 2007-07-07
Infrastructure and Operations Plan | bar: 2007-06-07 to 2007-10-07; 2008-02-01 to 2008-03-01
TRAVEL WARNING AND INFORMATION SYSTEMS (TWIS)
Develop Criteria | bar: 2006-10-06 to 2006-12-06
Data Collection | bar: 2006-12-06 to 2007-02-07
Apply Criteria | bar: 2007-02-07 to 2007-07-07
Technology Alternatives | bar: 2007-02-07 to 2007-07-07
Infrastructure and Operations Plan | bar: 2007-06-07 to 2007-10-07; 2008-02-01 to 2008-03-01
TRAFFIC SIGNAL SYSTEMS (TSS)
Develop Criteria | bar: 2006-10-06 to 2006-12-06
Data Collection | bar: 2006-10-06 to 2007-02-07
Apply Criteria | bar: 2007-02-07 to 2007-07-07
Technology Alternatives | bar: 2007-02-07 to 2007-07-07
Infrastructure and Operations Plan | bar: 2007-06-07 to 2007-10-07; 2008-02-01 to 2008-03-01
| 2006-07-06 | 2006-08-06 | 2006-09-06 | 2006-10-06 | 2006-11-06 | 2006-12-06 | 2007-01-07 | 2007-02-07 | 2007-03-07 | 2007-04-07 | 2007-05-07 | 2007-06-07 | 2007-07-07 | 2007-08-07 | 2007-09-07 | 2007-10-07 | 2007-11-07 | 2007-12-01 | 2008-01-01 | 2008-02-01 | 2008-03-01 | 2008-04-01 | 2008-05-01
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Legend
SPT - Live Meeting | bar: 2006-07-06
SPT - Teleconference | bar: 2006-07-06
Stakeholder Workshop (Tentative) | bar: 2006-07-06
Stakeholder Workshop 1: Review planning goals and criteria; review preliminary concepts of operation
Stakeholder Workshop 2: Review/select planning methodology; review examples of criteria application and technology alternatives assessment
Stakeholder Workshop 3: Review results of technology alternatives assessment; review approach to infrastructure and operations plans
Stakeholder Workshop 4: Review draft infrastructure and operations plans
Stakeholder Workshop 5: Review final infrastructure and operations plans; review how plans will be incorporated into statewide transportation planning process; explain/train use of methodology going forward
Note on E1: gcrowson: ITS Forum (October 31, 2006)
Note on K1: gcrowson: SmartWays Annual Meeting (March/April 2007)
Note on Q1: gcrowson: ITS Forum (October 2006)
Note on V1: gcrowson: SmartWays Annual Meeting (March/April 2008)